## Worksheet
ID | Title | Priority | Description | Start Date | End Date | Assign To | Milestone | Status
1 | Figma Designing | High | First Of We have to Start Work On the Figma Designing We have to create a Figma File of All Pages. | 2023-10-06 00:00:00 | 2023-10-26 00:00:00 | Harshil Patel,Tejas Patel, | UI/UX Designing | Review
2 | Frontend Development | Medium | In this task After Completing Figma File We Have to Start work on Frontend Develoepr. We Have to Design all the pages as per Figma File. | 2023-10-27 00:00:00 | 2023-11-27 00:00:00 | Harshil Patel,Tejas Patel, | Frontend Development | In Progress
3 | Backend Development | High | After Completing the Frontend We Have to Start Work On the Backend Development. | 2023-11-27 00:00:00 | 2023-12-31 00:00:00 | Harshil Patel,Tejas Patel, | Backend Development | Todo